## Sheet1
Technoter BurnDownChart
Project | Story | Task | Prediction | 2014-06-14 | 2014-06-13 | 2014-06-12 | 2014-06-11 | 2014-06-10 | 2014-06-09 | 2014-06-07 | 2014-06-06 | 2014-06-05 | 2014-06-04 | 2014-06-03 | 2014-06-02
ScrumMaster1_David | Pengumpulan Requirements | Pengumpulan user requirements dan pembuatan slide | 6 | [9 empty] | 3 | 2 | 1
|  | Pengumpulan system requirements dan pembuatan slide | 6 | [9 empty] | 3 | 2 | 1
|  | Pengumpulan functional requirements dan pembuatan slide | 6 | [9 empty] | 3 | 2 | 1
0
ScrumMaster2_Johan | Pembuatan Design | Prototype tampilan awal | 8 | [8 empty] | 2 | 0 | 0 | 0
|  | Prototype tampilan menu | 12 | [8 empty] | 3 | 0 | 0 | 0
|  | Diagram Alur Kerja | 8 | [8 empty] | 2 | 0 | 0 | 0
ScrumMaster3_ | Pembuatan Slide index.jade | Requirements | 6 | [9 empty] | 2 | 0 | 0
|  | Design | 8 | [9 empty] | 0 | 0 | 0
|  | Graphic | 6 | [9 empty] | 0 | 0 | 0
ScrumMaster4_ | Mempercantik Slide | Stylus | 2 | [9 empty] | 0 | 0 | 0
|  | JavaScript | 1 | [9 empty] | 0 | 0 | 0
2
Ideal - Remaining efforts in uninterrupted working hours |  |  | 69 | 63.25 | 57.5 | 51.75 | 46 | 40.25 | 34.5 | 28.75 | 23 | 17.25 | 11.5 | 5.75 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 11 | 6 | 3